## Project Planner
Project Title
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
initiating | 1 | 7 | 1 | 7 | 100%
Appoint a project manager | 1 | 1 | 1 | 1 | 100%
Develop project charter | 2 | 4 | 2 | 4 | 100%
Meet with the teammates | 6 | 2 | 6 | 2 | 100%
planning | 8 | 8 | 8 | 8 | 100%
Write the description about the scope plan | 8 | 2 | 8 | 2 | 100%
Create WBS and schedule | 10 | 1 | 10 | 1 | 100%
Write design system components | 11 | 2 | 11 | 2 | 100%
Create a gantt chart | 11 | 4 | 11 | 4 | 100%
Planning user interface design | 13 | 3 | 13 | 3 | 100%
Design tasks | 16 | 15 | 16 | 15 | 100%
Design the software components | 16 | 6 | 16 | 6 | 100%
Design the website layout | 22 | 6 | 22 | 6 | 100%
Design a list used for data analysis | 28 | 3 | 28 | 3 | 100%
Executing | 31 | 20 | 31 | 20 | 100%
Database integration | 31 | 5 | 31 | 5 | 100%
Making the website compatible to all devices | 36 | 3 | 36 | 3 | 100%
Check the data analysis | 39 | 2 | 39 | 2 | 100%
Creating the background query bank | 41 | 10 | 41 | 10 | 100%
Making query which will get the suburb data | 41 | 2 | 41 | 2 | 100%
Making query which will get the database for the pricing | 43 | 2 | 43 | 2 | 100%
Making query which would be looking for the key words from the database | 45 | 1 | 45 | 1 | 100%
Making query which will provide data for the neighborhood | 46 | 2 | 46 | 2 | 100%
Making query which will be looking for cleanliness | 46 | 3 | 46 | 3 | 100%
Designing how the graph would be represented | 47 | 3 | 47 | 3 | 100%
Designing how the data would be shown in the interface | 48 | 3 | 48 | 3 | 100%
Testing | 51 | 5 | 51 | 5 | 100%
Document test cases for all Subsystems | 51 | 2 | 51 | 2 | 100%
Gather test data based on iteration | 52 | 2 | 52 | 2 | 100%
System analysts perform test | 52 | 3 | 52 | 3 | 100%
Show the client his first deliverables | 53 | 2 | 53 | 2 | 100%
Perform user acceptance testing procedures | 53 | 2 | 53 | 2 | 100%
Write reports of test results | 55 | 1 | 55 | 1 | 100%
Controlling | 56 | 3 | 56 | 3 | 100%
Keep updates the Status | 56 | 2 | 56 | 2 | 100%
Update plans | 58 | 1 | 58 | 1 | 100%